# QuickBite – Assignment 2 Working Document

COMP 354 – Agile Software Development in Practice

Purpose: This is a shared working document to keep the team on the same page. It records our current decisions, what each assignment part depends on, and what needs to be completed next. The final report and GitHub/GitHub Projects evidence will be prepared separately.

# 1. Team Setup – Part A

| Team Member | Scrum Role | Main Assignment Area |
| --- | --- | --- |
| Dhruv | Scrum Master + Developer | Part A + Part E + GitHub coordination |
| Karim | Product Owner + Developer | Part B + Part F |
| Ray | Developer | Part C + Part D |
| Jou | Developer | Part G + Part H + Agile Reflection |

All four members are Developers and must make a meaningful technical contribution during the Sprint. The assignment-area division above is mainly for organizing the report/artifacts; connected Scrum activities still involve the team.

# 2. Initial Product Backlog – Part B

For the Product owner part B, please just go through the 12 PBIs we have and choose the top 5 you think are most important and give a short reason for each. Also check if the priorities/order I gave look good to you. If you think something should be higher or lower, just mention what you would change and why for the report

| ID | PBI | User Story | Acceptance Criteria | Current Order | Estimate |
| --- | --- | --- | --- | --- | --- |
| PBI-01 | Browse Restaurants | As a customer, I want to browse participating restaurants so that I can choose where to order from. | Participating restaurants are displayed; each shows its name and basic information; customer can select a restaurant. | 1 – High | 2 SP |
| PBI-02 | View Restaurant Menu | As a customer, I want to view a restaurant's menu so that I can decide what to order. | Selected restaurant's menu is displayed; menu shows item name, price and availability; only that restaurant's items are shown. | 2 – High | 3 SP |
| PBI-03 | Add Items to Order | As a customer, I want to add menu items to my order so that I can purchase them. | Customer can add available items; quantity can be selected; added items appear in the current order; unavailable items cannot be added. | 3 – High | 3 SP |
| PBI-04 | View and Modify Order | As a customer, I want to review and modify my order before submitting it so that I can correct mistakes. | Customer can see selected items and quantities; quantities can be changed; items can be removed; order total updates. | 4 – High | 3 SP |
| PBI-05 | Select Pickup Time | As a customer, I want to select a pickup time so that I know when to collect my order. | Customer can choose from available pickup times; a pickup time is required before ordering; selected time is shown with the order. | 5 – High | 3 SP |
| PBI-06 | Place Order | As a customer, I want to place my completed order so that the restaurant can prepare it. | Required information must be present; submitted order reaches the restaurant; customer receives confirmation; order gets an initial status. | 6 – High | 5 SP |
| PBI-07 | View Order Status | As a customer, I want to view my order status so that I know when my food is ready. | Customer can access the placed order; current status is displayed; status reflects restaurant updates. | 7 – Medium | 3 SP |
| PBI-08 | View Incoming Orders | As a restaurant employee, I want to view incoming orders so that I know what needs to be prepared. | Employee can see submitted orders; relevant order details and pickup time are displayed; orders show their current status. | 8 – Medium | 3 SP |
| PBI-09 | Update Order Status | As a restaurant employee, I want to update an order's status so that customers know its progress. | Employee can update Received → Preparing → Ready for Pickup → Completed; new status is saved; customer sees the update. | 9 – Medium | 3 SP |
| PBI-10 | Handle Unavailable Menu Items | As a restaurant employee, I want to mark menu items unavailable so that customers cannot order items we cannot provide. | Employee can mark an item unavailable; status is visible to customers; unavailable item cannot be added to a new order. | 10 – Medium | 3 SP |
| PBI-11 | Order Data Persistence | As the system, order information should be stored so that orders and their current status remain available. | Submitted order data is stored; stored orders can be retrieved; status changes remain after refresh/reload. | 11 – Medium | 5 SP |
| PBI-12 | Modify Pickup Time Within 15 Minutes | As a customer, I want to change my pickup time shortly after ordering so that I can adjust it if my plans change. | Customer can change pickup time within 15 minutes of ordering; new time is saved; after 15 minutes the change is disabled/rejected. | 12 – Low | 5 SP |

# 3. Product Owner

Review the 12 PBIs and finalize the Product Backlog order from 1–12.

Choose/finalize the top five PBIs and write a short reason explaining why each is a high priority.

Review the user stories, acceptance criteria, and story-point estimates; suggest changes if needed.

Help finalize a practical Definition of Done for the Sprint.

Share the finalized Part B information with the member handling Part C, because Sprint Planning must select PBIs from this Product Backlog.

Part F will be completed later, after the Sprint Plan exists and the new pickup-time/workload requirement is introduced.

# 4. Part Dependencies / Team Coordination

| Part | Depends On | Why |
| --- | --- | --- |
| Part C – Sprint Planning | Part B | Selected Sprint PBIs must come from the finalized Product Backlog. |
| Part D – Working Increment | Part C | Implementation must follow the Sprint Goal and Sprint Backlog. |
| Part E – Daily Scrums | Parts C/D | Daily Scrums track progress, impediments and adaptations toward the Sprint Goal. |
| Part F – Requirement Change | Parts B/C and Sprint progress | The new workload-based pickup-time requirement must be compared with the existing backlog and Sprint. |
| Part G – Sprint Review | Part D | Stakeholder feedback must be based on the actual working Increment. |
| Part H – Retrospective | Actual Sprint experience | Improvement actions should come from what actually happened during the Sprint. |
| Agile Reflection | Parts D–H | Reflection must use concrete evidence from the team's actual work. |

Option2:

Part C — Sprint Planning

Sprint Goal

Sprint Goal: Create a basic working customer ordering flow that allows a customer to browse restaurants, view a menu, add and modify items in an order, select a pickup time, and successfully place the order.

Selected PBIs

| PBI | Product Backlog Item | Estimate |
| --- | --- | --- |
| PBI-01 | Browse Restaurants | 2 SP |
| PBI-02 | View Restaurant Menu | 3 SP |
| PBI-03 | Add Items to Order | 3 SP |
| PBI-04 | View and Modify Order | 3 SP |
| PBI-05 | Select Pickup Time | 3 SP |
| PBI-06 | Place Order | 5 SP |
| Total |  | 19 SP |

These PBIs were selected because they work together to create one connected customer ordering flow.

Team Capacity

Our team consists of four Developers. For this Sprint, we selected 19 story points of work. We considered the time needed for implementation, UI work, testing, integration, code review, and documentation.

Engineering Tasks

PBI-01 — Browse Restaurants

- Create restaurant data

- Create restaurant-list interface

- Display restaurant name and basic information

- Allow customer to select a restaurant

- Test restaurant browsing and selection

PBI-02 — View Restaurant Menu

- Create menu-item data

- Connect menu items to restaurants

- Create menu interface

- Display item name, price, and availability

- Display only the selected restaurant's menu

PBI-03 — Add Items to Order

- Create order/cart structure

- Implement Add to Order

- Allow quantity selection

- Display added items

- Prevent unavailable items from being added

- Test adding items and quantities

PBI-04 — View and Modify Order

- Create order-summary interface

- Display selected items and quantities

- Allow quantity changes

- Allow items to be removed

- Update the order total

- Test modifying and removing items

PBI-05 — Select Pickup Time

- Create a simple list of available pickup times

- Add pickup-time selection to the ordering flow

- Save the customer's selected pickup time with the order

- Prevent order submission if no pickup time is selected

- Test pickup-time selection and validation

PBI-06 — Place Order

- Connect the cart/order information with the selected pickup time

- Implement order submission

- Store the submitted order

- Give the order an initial Received status

- Display a successful order confirmation

- Test valid and incomplete order submissions

- Integrate the complete customer ordering flow

Sprint Backlog

To Do → In Progress → Code Review/Testing → Done

All selected PBIs and their engineering tasks will be added to the Sprint Backlog and moved through these stages as the Sprint progresses.

Technical Work Distribution

| Team Member | Technical Work |
| --- | --- |
| Dhruv | PBI-01 — Restaurant browsing and selection |
| Karim | PBI-02 — Restaurant menu |
| Rayan | PBI-03 — Add items/cart |
| Jouliana | PBI-04 — View and modify order |

All four team members will contribute to implementation, testing, integration, and code review.

Part D — Execute the Sprint and Produce a Working Increment

Working Increment

During the Sprint, the team will implement a small, but functional Quick Bite customer ordering flow based on the Sprint Goal. The Increment will allow customers to:

- Browse participating restaurants

- Select a restaurant

- View the selected restaurant's menu

- Add available items to an order

- Select quantities

- View and modify the order

- Remove items from the order

- See the updated order total

- Select an available pickup time

- Submit the completed order

- Receive an order confirmation with an initial Received status

The completed functionality will be integrated into one usable customer ordering flow rather than separate unfinished features. This is what the assignment requires for the Increment. Git and Branches

The team will use the shared QuickBite GitHub repository. Each team member will work on an appropriate feature branch before integrating their work into the main branch.

- feature/restaurant-browsing

- feature/menu

- feature/cart

- feature/order-flow

Commits

Each team member will make meaningful commits that clearly describe the completed work, such as:

- Add restaurant browsing functionality

- Implement restaurant menu display

- Add cart and quantity functionality

- Implement order modification

- Add pickup time selection

- Implement order submission and confirmation

Integration and Code Review

Before work is merged into the main branch, another team member will review the changes. The team will use pull requests to review and integrate the different features into one working Increment.

Testing

The team will test the functionality against the acceptance criteria. Testing will include:

- Restaurant list displays correctly

- Customer can select a restaurant

- Correct menu is displayed

- Available items can be added

- Unavailable items cannot be added

- Quantities can be changed

- Items can be removed

- Order total updates correctly

- Pickup time can be selected

- Order cannot be submitted without required information

- Valid order can be submitted

- Confirmation and Received status are displayed

Sprint Backlog Updates

As development progresses, tasks on GitHub Projects will move through:

Todo → In Progress → In Review → Done

The Sprint Backlog will be updated throughout the Sprint to show the team's actual progress.

Definition of Done

A PBI is considered Done when:

- Its acceptance criteria are satisfied

- Implementation is complete

- Code is committed to GitHub

- Code is reviewed by another team member

- The feature is integrated with the Increment

- Required testing passes

- The GitHub task is moved to Done

Technical Contribution

All four team members will make meaningful technical contributions through implementation, testing, integration, and code review.

The assignment specifically requires the team to actually use branches, meaningful commits, integration, code review, testing, Sprint Backlog updates, and the Definition of Done during development.

Option3:

Part G — Sprint Review

Sprint Review

At the end of the Sprint, the team will demonstrate the working QuickBite Increment to the stakeholders. The demonstration will show the completed customer ordering flow, including browsing restaurants, viewing menus, adding and modifying items, selecting a pickup time, and placing an order.

Stakeholder Feedback

During the Sprint Review, the team will collect at least three pieces of stakeholder feedback.

| # | Stakeholder Feedback | Decision | Backlog Action |
| --- | --- | --- | --- |
| 1 | Stakeholders want pickup times to better reflect the restaurant's current workload. | Accept | Modify PBI-05 to improve pickup-time availability based on restaurant capacity. |
| 2 | Stakeholders want the order confirmation to clearly show the restaurant, items, total, and pickup time. | Accept | Modify PBI-06 to include more information on the confirmation screen. |
| 3 | Stakeholders want customers to easily see the current status of their order after placing it. | Accept | Keep and prioritize PBI-07, View Order Status, for the next Sprint. |

Backlog Adaptation

Based on the Sprint Review feedback, the Product Backlog will be updated. PBI-05 and PBI-06 will be modified to include the accepted improvements, and PBI-07 will receive higher priority for the next Sprint.

The Sprint Review demonstrates the Agile feedback cycle:

Working Increment → Stakeholder Feedback → Learning → Product Backlog Adaptation

Part H — Sprint Retrospective

What Went Well

- The team divided the technical work between the four Developers.

- GitHub Projects helped the team organize and track Sprint tasks.

- Feature branches and meaningful commits helped keep the development work organized.

- Breaking PBIs into smaller engineering tasks made the work easier to manage.

What Did Not Go Well

- Some tasks took longer than expected.

- Team members depended on each other's work, which sometimes slowed progress.

- The GitHub Project board was not always updated immediately when work changed.

- Testing and code review could have started earlier.

What Slowed the Team Down

Dependencies between tasks slowed the team because some functionality needed to be completed before another team member could continue their work.

What Helped Collaboration

Using the shared GitHub repository and GitHub Projects helped everyone see the Sprint tasks, current progress, and completed work.

Definition of Done

The Definition of Done helped the team understand that a task was not finished just because the code was written. The work also needed to satisfy the acceptance criteria, be tested, reviewed, integrated, and updated on the project board.

Improvement Actions for the Next Sprint

- Update the GitHub Project board before each Daily Scrum so everyone has an accurate view of the Sprint progress.

- Start testing and code review earlier instead of leaving them until the end of the Sprint.

## Agile Reflection

### 1. Incremental Delivery

The team used incremental delivery by dividing the QuickBite system into smaller PBIs and engineering tasks. Instead of trying to build the entire application at once, the team worked on smaller features that could be integrated into a working Increment.

### 2. Responding to Change

During the Sprint, the team had to respond to changes in the requirements, especially the new requirement related to pickup-time availability. The Product Backlog and Sprint work were adapted to consider the new requirement instead of ignoring the change.

### 3. Stakeholder Collaboration

The Sprint Review allowed stakeholders to see the working Increment and provide feedback. The team used this feedback to decide what should be modified, clarified, or prioritized in the Product Backlog.

### 4. Technical Quality

The team used GitHub branches, meaningful commits, testing, code review, and integration to support technical quality. The Definition of Done also helped ensure that work was properly completed before being considered Done.

### 5. Continuous Improvement

The Sprint Retrospective helped the team identify problems and ways to improve. For the next Sprint, the team plans to update the project board more consistently and begin testing and code review earlier.